## Slide 1: Neighborhood Update RW-21 Area Remedial Design/Remedial Action
0
–
Operable Unit 3 – Bethpage, New York October 13, 2016
©Northrop Grumman 2016
Approved for public release, NG16-2042, 10/12/16

## Slide 2
Overview – Why are we here?
New York State has approved Northrop Grumman’s plan to clean up groundwater quality, which will benefit the community
Project Overview
Review of Schedule
Response to Comments
Project contact for more information
Northrop Grumman, New York State DEC and DOH,
and Nassau County DOH representatives
are here to answer your questions
Approved for public release, NG16-2042, 10/12/16

## Slide 3: Project area
Proposed Remedial Well
Approved Boring/Monitoring Well
Plume Contours, ug/L
  500
  1,000 5,000
Width of Area of VOC Mass
Approved Remedial Well
Approved for public release, NG16-2042, 10/12/16

## Slide 4
  Below-ground vaults for wells installed to extract groundwater
  Groundwater pumped to treatment system in buried pipes
  Removes contamination from the groundwater
  Includes water and air treatment, and other required equipment
  Clean water from treatment system pumped to new recharge basin near Arthur Avenue or to the existing basin on Arthur Avenue
Key Elements of the Cleanup System
Three Groundwater Remedial Wells
Treatment System
Discharge Pipe
Approved for public release, NG16-2042, 10/12/16

## Slide 5
Project Overview
New Building Near GM-38 Treatment Plant
NYSDEC- approved, TOB permitted well
New buried pipe location
Approved for public release; NG16-2042, 10/12/16
©Northrop Grumman 2016
New Treatment Building
RW-21
RW-20
RW-22
NYSDEC-approved, TOB permit-pending well
Proposed
New Basin
New buried treated water line and flow direction
Existing Navy GM-38 buried treated water line and flow direction
Arthur Avenue Basin
Notes: Mention 2 phases of pipe installation:
Install pipe stubs and vaults at the same time as the remedial well
Install remainder of pipes, install electric, pumps, plumbing, and complete development of the remedial well.

## Slide 6
Install VPBs & Monitoring Wells
Purchase Remedial System Equipment
Install RW-21 & RW-22
Install RW-20
Build New Basin
Remedial Design
Build Treatment Plant
Install Piping & Vaults
Install
Discharge Line
Design Studies
(Borings & Surveying)
Permitting & Access Agreements
Expedited Schedule
Start
Up
OCT
JUL
APR
JUL
APR
JAN
2017
2016
CONSTRUCTION
PERMITTING
& DESIGN
Completing some steps in parallel reduces timeline & community disruption
Water won’t be pumped through system until Start-Up!
Approved for public release, NG16-2042, 10/12/16

## Slide 7
  Safety and Security
  Temporary Power, Plans to Mitigate Noise, Dust, and Vibration
  Site Restoration
  Engagement with Bethpage School District transportation officials
  Source of Electric Power
  Vault Excavation/Installation Method
  Utilities
  Coordination for Use of Municipal Lot near St. Martin of Tours
  Site Restoration
Summary of Comment Topics
RW-20
Treatment System
  Capacity
  Maintenance Activities
Basins
Approved for public release, NG16-2042, 10/12/16

## Slide 8
William St.
Broadway
N. Windhorst Ave.
Transplanted Trees
Tree
Requiring
Pruning
Proposed Temporary Power
Pole and Service Relocation
Re-Configuration of RW-20 Work Zone
We reduced the work zone and relocated well on to William Street. This solution no longer blocks traffic on Broadway, but requires an additional 4 weeks.
N
Smaller work area reduces impact to community.
Proposed Well
Approved for public release; NG16-2042, 10/12/16
©Northrop Grumman 2016

## Slide 9: New RW-20 Well and Vault Location
William Street
Well Vault Access Hatch
Side lawn of 160 Broadway
Well Vault Outside Edge
Sidewalk
Town Right-of-Way
Well Vault Access Hatch
Re-Located Gas Line
Approved for public release, NG16-2042, 10/12/16

## Slide 10
Our plan includes health, safety and security measures to protect our community and our site workers
    SAFETY work materials will be contained; excess materials removed each day
    SECURITY for workers and residents throughout the project (including while school in session)
    CONTROLS minimize inconvenience to residents and businesses
    WORK HOURS are done in accordance with town code.
    COMMUNITY ENGAGEMENT open door policy with residents, officials
Goal: Expedited Schedule to Reduce Neighborhood Impact
Safety, Security, Controls, Work Hours, Engagement
Established
bi-weekly project review meetings with NY State and Town experts
    All work is coordinated with NYSDEC, State and County DOHs, and Town of Oyster Bay
Approved for public release; NG16-2042, 10/12/16
©Northrop Grumman 2016

## Slide 11
Contact Information
Mr. Steven Scharf, P.E. Project Manager NYSDEC Main Office: (518) 402-9620, Ext 3. E-mail: steven.scharf@dec.ny.gov
Mr. William Fonda Citizen Participation Specialist NYSDEC Public Affairs & Education Main Office: (631) 444-0347 E-mail: Bill.Fonda@dec.ny.gov
Mr. Steven Karpinski NYS Department of Health Main Office: (518) 402-7853 E-mail: steven.karpinski@health.ny.gov
If you have questions or concerns, please contact these New York State project representatives:
©Northrop Grumman 2016
Approved for public release, NG16-2042, 10/12/16

## Slide 12
Contact Information
Ms. Dianne Baumert-Moyik Communications Northrop Grumman Cell Phone: (516) 754-2645 E-mail: Dianne.Baumert-Moyik@ngc.com
If you wish to contact Northrop Grumman directly, please contact:
Please sign the attendance sheet with your email and phone number as you leave, so that we can provide you with updates on project status.
©Northrop Grumman 2016
Approved for public release, NG16-2042, 10/12/16

## Slide 13: Thank You
Please pick up a fact sheet as you leave
©Northrop Grumman 2016
Approved for public release, NG16-2042, 10/12/16