## Sheet1
Sample Plan and Schedule
| Activity Name | Description | Source(s) Addressed | Outcome(s) Expected | Resource(s) Needed | Target Start Date | Target End Date
Activity 1 | Septic Education | Develop and mail out education materials for septic systems. | wastewater | education and engagement from homeowners on proper septic maintenance | Staff time, Funds to print | 2026-04-01 | 2027-02-01
Activity 1A | Develop materials | Develop educational materials for nitrogen pollution linked to septic systems for residential and business/commercial properties. | wastewater | materials to distribute to engage homeowners | Staff time, Funds to print | 2026-04-01 | 2027-12-31
Activity 1B | Mail materials | Send out septic materials in school tax bill. | wastewater | engagement of homeowners | Staff time | 2027-01-01 | 2028-02-01
Activity 2 | Municipality's Fertilizer Use - Stop | No fertilizer use on municipal properties. Draft memo and send out to DPW and facilities. | fertilizer | reduction of 2.0 lbs/day of nitrogen (additional cost savings) | Memo to staff | 2027-04-01 | 2028-05-01
Activity 3 | Residential Fertilizer Use | Develop and mail out education materials for fertilizer use on residential properties. | fertilizer | education and engagement from homeowners on proper fertilizer use | Staff time, Funds to print | 2027-04-01 | 2028-07-31
Activity 3A | Develop materials | Develop education materials for fertilizer use on residential properties to limit nitrogen leaching and runoff. | fertilizer | materials to distribute to engage homeowners | Staff time, Funds to print | 2027-04-01 | 2028-05-31
Activity 3B | Mail materials | Mail educational materials with property tax bill. | fertilizer | engagement of homeowners | Staff time | 2027-06-01 | 2028-07-31
Activity 4 | Municipal Fertilizer Regulation | Enact fertilizer reduction legislation based on research into LINAP Recommendations, other local fertilizer laws, and town board input. | fertilizer | reduction of nitrogen fertilizer load | Staff time, legal time, enforcement discussions | 2027-01-01 | 2027-12-31
Activity 5 | Nitrogen Removal Upgrade WWTP #4 | Upgrade WWTP#4 with nitrogen removal. | wastewater | removal of 2.0 lbs/day of nitrogen from effluent into the receiving waterbody | Staff time, Funds for contractors, Grant applications, Funds for grant match | 2026-10-01 | 2027-12-31
Activity 5A | Apply for grant funds for feasibility study at WWTP #4. | Apply to grant program for funds. | wastewater | grant application | Staff time | 2026-10-01 | 2027-12-31
Activity 5B | Feasibility Study for Nitrogen Reduction at WWTP #4 | Conduct a feasibility study to determine what type of nutrient removal can occur at WWTP #4. | wastewater | determination on type of technology that can be constructed at WWTP #4 to remove at least an additional 2.0 lbs/day of nitrogen. | Staff time, $$ for contractors | 2027-01-01 | 2028-12-31
Activity 5C | Develop a design/plan to implement the results of WWTP #4 feasibility study. | Issue an RFP for the design of the nutrient removal practice determined in Action 5B. | wastewater | design/plan for nutrient removal construction at WWTP #4 | Staff time, $$ for contractors | 2027-01-01 | 2028-12-31
Activity 5D | Apply for grant funds to construct upgrade to WWTP #4 | Apply to NYS WQIP grant program for funds to construct nutrient removal at WWTP #4. | wastewater | grant application | Staff time | 2027-04-01 | 2027-06-30
Activity 5E | RFP to construct upgrade to WWTP #4. | Issue RFP for construction of nutrient removal upgrade to WWTP #4 | wastewater | RFP for construction | Staff time | 2026-07-01 | 2027-12-31
Activity 5F | Construct upgrade to WWTP #4. | Construct nutrient removal upgrade to WWTP #4 | wastewater | construct nutrient removal at WWTP #4 to remove 2.0 lbs/day of nitrogen. | Staff time, grant match $$ | 2027-01-01 | 2028-12-31
Activity 6 | Review Stormwater Guidance. | Review municipal stormwater guidance to ensure it is up to date and being followed. | stormwater | potential updates to guidance | Staff time | 2027-04-01 | 2027-06-30
Activity 7
Activity 8
Activity 9
Activity 10